## Sheet1
HOST | WORK FLOW | NEXT STEP | OS MAKE | Criticality | ENVSTATUS | PRE UPTIME | SNOW SUPPORT BY | SNOW OWNED BY | CR ID | PATCH WINDOW (GMT) Start Time | PATCH WINDOW (GMT)End Time | PATCH WINDOW (HKT) Start Time | PATCH WINDOW (HKT)End Time | PRE-REL | PRE STAT | W/O LVM SNAP | PATCH STAT | POST STAT | TARGT-REL | COMMENT
hkwvasapp525 | Go | Patch | Windows2019 VMware | 4-High | DROperational | 32 | INFRA SERVER - WINDOWS - ATOS PROD TSO SUP | ServiceNow ITOM Visibility PROD TSO SUP | CHG0279579 | 2023-08-09 14:30 | 2023-08-09 18:30 | 2023-08-09 22:30 | 2023-08-10 02:30 |  | Green | No | NA | NA | latest | Scheduled for Patch
hkwvasapp526 | Go | Patch | Windows2019 VMware | 4-High | DROperational | 32 | INFRA SERVER - WINDOWS - ATOS PROD TSO SUP | ServiceNow ITOM Visibility PROD TSO SUP | CHG0279579 | 2023-08-09 14:30 | 2023-08-09 18:30 | 2023-08-09 22:30 | 2023-08-10 02:30 |  | Green | No | NA | NA | latest | Scheduled for Patch
hkwvapapp525 | Go | Patch | Windows2019 VMware | 4-High | PrdOperational | 38 | INFRA SERVER - WINDOWS - ATOS PROD TSO SUP | ServiceNow ITOM Visibility PROD TSO SUP | MW_2023-32 | 2023-08-10 14:30 | 2023-08-10 18:30 | 2023-08-10 22:30 | 2023-08-11 02:30 |  | Green | No | NA | NA | latest | Scheduled for Patch
hkwvapapp526 | Go | Patch | Windows2019 VMware | 4-High | PrdOperational | 38 | INFRA SERVER - WINDOWS - ATOS PROD TSO SUP | ServiceNow ITOM Visibility PROD TSO SUP | MW_2023-32 | 2023-08-10 14:30 | 2023-08-10 18:30 | 2023-08-10 22:30 | 2023-08-11 02:30 |  | Green | No | NA | NA | latest | Scheduled for Patch
hkwvapapp304 | Go | Patch | Windows2012 VMware | 5-Catastrophic | PrdOperational | 25 | INFRA SERVER - WINDOWS - ATOS PROD TSO SUP | ESIGCAP PROD TSO SUP | MW_2023-32 | 2023-08-11 05:00 | 2023-08-11 09:00 | 2023-08-11 13:00 | 2023-08-11 17:00 |  | Green | No | NA | NA | latest | Scheduled for Patch
hkwvasmsu011 | Go | Patch | Windows2016 VMware | 5-Catastrophic | DROperational | 25 | INFRA SERVER - WINDOWS - ATOS PROD TSO SUP | INFRA-STORAGE-SAN PROD TSO SUP | LEAP_PB | 2023-08-11 08:00 | 2023-08-11 12:00 | 2023-08-11 16:00 | 2023-08-11 20:00 |  | Green | No | NA | NA | latest | Scheduled for Patch
hkwpapsfb003 | Go | Patch | Windows2012 R640 | 4-High | PrdOperational | 25 | INFRA SERVER - WINDOWS - ATOS PROD TSO SUP | SKYPE FOR BUSINESS PROD TSO SUP | MW_2023-32 | 2023-08-11 21:00 | 2023-08-12 01:00 | 2023-08-12 05:00 | 2023-08-12 09:00 |  | Amber | No | NA | NA | latest | PRE: Server already patched but Reboot pending.
hkwvapapp362 | Go | Patch | Windows2012 VMware | 4-High | PrdOperational | 25 | INFRA SERVER - WINDOWS - ATOS PROD TSO SUP | SKYPE FOR BUSINESS PROD TSO SUP | MW_2023-32 | 2023-08-11 21:00 | 2023-08-12 01:00 | 2023-08-12 05:00 | 2023-08-12 09:00 |  | Amber | No | NA | NA | latest | PRE: Server already patched but Reboot pending.
hkwvasapp603 | Pause | Pre | Windows2019 VMware | 4-High | PrdOperational | 17 | INFRA SERVER - WINDOWS - ATOS PROD TSO SUP | INFORMATION RIGHTS MANAGEMENT PROD TSO SUP | MW_2023-32 | 2023-08-12 | 2023-08-12 04:00 | 2023-08-12 08:00 | 2023-08-12 12:00 |  | Red | No | NA |  | latest | PRE: EvaluateKB failed. Exception from HRESULT : 0x80240438
hkwpassfb003 | Go | Patch | Windows2012 R640 | 4-High | DROperational | 32 | INFRA SERVER - WINDOWS - ATOS PROD TSO SUP | SKYPE FOR BUSINESS DR TSO SUP | MW_2023-32 | 2023-08-12 01:00 | 2023-08-12 05:00 | 2023-08-12 09:00 | 2023-08-12 13:00 |  | Amber | No | NA |  | latest | PRE: Server already patched but Reboot pending.
hkwxassfb01 | Go | Patch | Windows2012 R630 | 4-High | DROperational | 32 | INFRA SERVER - WINDOWS - ATOS PROD TSO SUP | SKYPE FOR BUSINESS DR TSO SUP | MW_2023-32 | 2023-08-12 01:00 | 2023-08-12 05:00 | 2023-08-12 09:00 | 2023-08-12 13:00 |  | Green | No | NA | NA | latest | Scheduled for Patch
hkwpdssql002 | Go | Patch | Windows2012 R640 | 4-High | DROperational | 32 | INFRA SERVER - WINDOWS - ATOS PROD TSO SUP | SKYPE FOR BUSINESS DR TSO SUP | MW_2023-32 | 2023-08-12 02:00 | 2023-08-12 06:00 | 2023-08-12 10:00 | 2023-08-12 14:00 |  | Amber | No | NA | NA | latest | PRE: Server already patched but Reboot pending.
hkwpdssql001 | Go | Patch | Windows2012 R640 | 4-High | DROperational | 31 | INFRA SERVER - WINDOWS - ATOS PROD TSO SUP | SKYPE FOR BUSINESS DR TSO SUP | MW_2023-32 | 2023-08-12 06:00 | 2023-08-12 10:00 | 2023-08-12 14:00 | 2023-08-12 18:00 |  | Amber | No | NA | NA | latest | PRE: Server already patched but Reboot pending.
hkwvapssp01 | Go | Patch | Windows2012 VMware | 4-High | PrdOperational | 80 | INFRA SERVER - WINDOWS - ATOS PROD TSO SUP | SSPORTAL PROD TSO SUP | MW_2023-32 | 2023-08-12 06:00 | 2023-08-12 12:00 | 2023-08-12 14:00 | 2023-08-12 20:00 |  | Amber | No | NA | NA | latest | PRE: Server already patched but Reboot pending.
hkwvapssp02 | Go | Patch | Windows2012 VMware | 4-High | PrdOperational | 87 | INFRA SERVER - WINDOWS - ATOS PROD TSO SUP | SSPORTAL PROD TSO SUP | MW_2023-32 | 2023-08-12 06:00 | 2023-08-12 12:00 | 2023-08-12 14:00 | 2023-08-12 20:00 |  | Amber | No | NA | NA | latest | PRE: Server already patched but Reboot pending.
hkwvapapp364 | Go | Patch | Windows2012 VMware | 4-High | PrdOperational | 31 | INFRA SERVER - WINDOWS - ATOS PROD TSO SUP | SKYPE FOR BUSINESS PROD TSO SUP | MW_2023-32 | 2023-08-12 09:00 | 2023-08-12 13:00 | 2023-08-12 17:00 | 2023-08-12 21:00 |  | Amber | No | NA | NA | latest | PRE: Server already patched but Reboot pending.
hkwvapftp01 | Go | Patch | Windows2012 VMware | 4-High | PrdOperational | 87 | INFRA SERVER - WINDOWS - ATOS PROD TSO SUP | PEOPLESOFT FTP PROD TSO SUP | MW_2023-32 | 2023-08-12 11:00 | 2023-08-13 02:00 | 2023-08-12 19:00 | 2023-08-13 10:00 |  | Green | No | NA | NA | latest | Scheduled for Patch
hkwvasapp364 | Go | Patch | Windows2012 VMware | 4-High | DROperational | 31 | INFRA SERVER - WINDOWS - ATOS PROD TSO SUP | SKYPE FOR BUSINESS DR TSO SUP | MW_2023-32 | 2023-08-12 13:00 | 2023-08-12 17:00 | 2023-08-12 21:00 | 2023-08-13 01:00 |  | Amber | No | NA | NA | latest | PRE: Server already patched but Reboot pending.
hkwvasctx092 | Go | Patch | Windows2019 VMware | 5-Catastrophic | DROperational | 13 | INFRA SERVER - WINDOWS - ATOS PROD TSO SUP | RPPBC MY DR TSO SUP | MW_2023-32 | 2023-08-12 14:00 | 2023-08-13 04:00 | 2023-08-12 22:00 | 2023-08-13 12:00 |  | Amber | No | NA | NA | latest | PRE: Server already patched but Reboot pending.
hkwvipapp003 | Go | Patch | Windows2012 VMware | 4-High | PrdOperational | 31 | INFRA SERVER - WINDOWS - ATOS PROD TSO SUP | VOPS-IVR-AVAYA4 PROD TSO SUP | MW_2023-32 | 2023-08-12 16:00 | 2023-08-13 00:30 | 2023-08-13 | 2023-08-13 08:30 |  | Green | No | NA | NA | latest | Scheduled for Patch
hkwpapsfb004 | Go | Patch | Windows2012 R640 | 4-High | PrdOperational | 31 | INFRA SERVER - WINDOWS - ATOS PROD TSO SUP | SKYPE FOR BUSINESS PROD TSO SUP | MW_2023-32 | 2023-08-12 17:00 | 2023-08-12 21:00 | 2023-08-13 01:00 | 2023-08-13 05:00 |  | Amber | No | NA | NA | latest | PRE: Server already patched but Reboot pending.
hkwvapapp363 | Go | Patch | Windows2012 VMware | 4-High | PrdOperational | 31 | INFRA SERVER - WINDOWS - ATOS PROD TSO SUP | SKYPE FOR BUSINESS PROD TSO SUP | MW_2023-32 | 2023-08-12 17:00 | 2023-08-12 21:00 | 2023-08-13 01:00 | 2023-08-13 05:00 |  | Amber | No | NA | NA | latest | PRE: Server already patched but Reboot pending.
hkwvasapp365 | Go | Patch | Windows2012 VMware | 4-High | DROperational | 31 | INFRA SERVER - WINDOWS - ATOS PROD TSO SUP | SKYPE FOR BUSINESS DR TSO SUP | MW_2023-32 | 2023-08-12 17:00 | 2023-08-12 21:00 | 2023-08-13 01:00 | 2023-08-13 05:00 |  | Amber | No | NA | NA | latest | PRE: Server already patched but Reboot pending.
hkwvasapp644 | Go | Patch | Windows2019 VMware | 4-High | DROperational | 31 | INFRA SERVER - WINDOWS - ATOS PROD TSO SUP | ICDD-AE TSO SUP, ICDD-ID TSO SUP, ICDD-SG TSO SUP, ICDD 001 DR TSO SUP, ICDD-FRIDAY TSO SUP, ICDD-PK TSO SUP, ICDD-IN TSO SUP, ICDD-HK TSO SUP, ICDD-MY TSO SUP, ICDD-SUNDAY TSO SUP | MW_2023-32 | 2023-08-12 18:00 | 2023-08-12 22:00 | 2023-08-13 02:00 | 2023-08-13 06:00 |  | Green | No | NA | NA | latest | Scheduled for Patch
hkwpassfb004 | Go | Patch | Windows2012 R640 | 4-High | DROperational | 31 | INFRA SERVER - WINDOWS - ATOS PROD TSO SUP | SKYPE FOR BUSINESS DR TSO SUP | MW_2023-32 | 2023-08-12 21:00 | 2023-08-13 01:00 | 2023-08-13 05:00 | 2023-08-13 09:00 |  | Amber | No | NA | NA | latest | PRE: Server already patched but Reboot pending.
hkwvapapp365 | Go | Patch | Windows2012 VMware | 4-High | PrdOperational | 31 | INFRA SERVER - WINDOWS - ATOS PROD TSO SUP | SKYPE FOR BUSINESS PROD TSO SUP | MW_2023-32 | 2023-08-13 01:00 | 2023-08-13 05:00 | 2023-08-13 09:00 | 2023-08-13 13:00 |  | Amber | No | NA | NA | latest | PRE: Server already patched but Reboot pending.
hkwpdpsql003 | Go | Patch | Windows2012 R640 | 4-High | PrdOperational | 31 | INFRA SERVER - WINDOWS - ATOS PROD TSO SUP | SKYPE FOR BUSINESS PROD TSO SUP | MW_2023-32 | 2023-08-13 02:00 | 2023-08-13 06:00 | 2023-08-13 10:00 | 2023-08-13 14:00 |  | Amber | No | NA | NA | latest | PRE: Server already patched but Reboot pending.
hkwvapapp366 | Go | Patch | Windows2012 VMware | 4-High | PrdOperational | 30 | INFRA SERVER - WINDOWS - ATOS PROD TSO SUP | SKYPE FOR BUSINESS PROD TSO SUP | MW_2023-32 | 2023-08-13 09:00 | 2023-08-13 13:00 | 2023-08-13 17:00 | 2023-08-13 21:00 |  | Amber | No | NA | NA | latest | PRE: Server already patched but Reboot pending.
hkwxapsfb01 | Go | Patch | Windows2012 R630 | 4-High | PrdOperational | 30 | INFRA SERVER - WINDOWS - ATOS PROD TSO SUP | SKYPE FOR BUSINESS PROD TSO SUP | MW_2023-32 | 2023-08-13 09:00 | 2023-08-13 13:00 | 2023-08-13 17:00 | 2023-08-13 21:00 |  | Green | No | NA | NA | latest | Scheduled for Patch
hkwvapmsu011 | Go | Patch | Windows2016 VMware | 5-Catastrophic | PrdOperational | 30 | INFRA SERVER - WINDOWS - ATOS PROD TSO SUP | INFRA-STORAGE-SAN NON-PROD TSO SUP | MW_2023-32 | 2023-08-13 10:00 | 2023-08-13 14:00 | 2023-08-13 18:00 | 2023-08-13 22:00 |  | Green | No | NA | NA | latest | Scheduled for Patch
hkwvapctx047 | Go | Patch | Windows2016 VMware | 4-High | PrdOperational | 87 | INFRA SERVER - WINDOWS - ATOS PROD TSO SUP | RAYCO PROD TSO SUP | MW_2023-32 | 2023-08-13 12:00 | 2023-08-13 16:00 | 2023-08-13 20:00 | 2023-08-14 |  | Amber | No | NA | NA | latest | PRE: Server already patched but Reboot pending.
hkwvisapp003 | Go | Patch | Windows2012 VMware | 4-High | DROperational | 30 | INFRA SERVER - WINDOWS - ATOS PROD TSO SUP | VOPS-IVR-AVAYA4 DR TSO SUP | MW_2023-32 | 2023-08-13 16:00 | 2023-08-13 20:00 | 2023-08-14 | 2023-08-14 04:00 |  | Green | No | NA | NA | latest | Scheduled for Patch
Formulas:
PATCH WINDOW (HKT) Start Time = [PATCH WINDOW (GMT) Start Time]+8/24
PATCH WINDOW (HKT)End Time = [PATCH WINDOW (GMT)End Time]+8/24

## Sheet3
hkwpdssql002
hkwpdssql001
hkwpdpsql003

## Sheet2
PATCH WINDOW (GMT) Start Time | PATCH WINDOW (GMT)End Time | PATCH WINDOW (HKT) Start Time | PATCH WINDOW (HKT)End Time
2023-08-09 14:30 | 2023-08-09 18:30 | 2023-08-09 22:30 | 2023-08-10 02:30
2023-08-09 14:30 | 2023-08-09 18:30 | 2023-08-09 22:30 | 2023-08-10 02:30
2023-08-10 14:30 | 2023-08-10 18:30 | 2023-08-10 22:30 | 2023-08-11 02:30
2023-08-10 14:30 | 2023-08-10 18:30 | 2023-08-10 22:30 | 2023-08-11 02:30
2023-08-11 05:00 | 2023-08-11 09:00 | 2023-08-11 13:00 | 2023-08-11 17:00
2023-08-11 08:00 | 2023-08-11 12:00 | 2023-08-11 16:00 | 2023-08-11 20:00
2023-08-11 21:00 | 2023-08-12 01:00 | 2023-08-12 05:00 | 2023-08-12 09:00
2023-08-11 21:00 | 2023-08-12 01:00 | 2023-08-12 05:00 | 2023-08-12 09:00
2023-08-12 | 2023-08-12 04:00 | 2023-08-12 08:00 | 2023-08-12 12:00
2023-08-12 01:00 | 2023-08-12 05:00 | 2023-08-12 09:00 | 2023-08-12 13:00
2023-08-12 01:00 | 2023-08-12 05:00 | 2023-08-12 09:00 | 2023-08-12 13:00
2023-08-12 02:00 | 2023-08-12 06:00 | 2023-08-12 10:00 | 2023-08-12 14:00
2023-08-12 06:00 | 2023-08-12 10:00 | 2023-08-12 14:00 | 2023-08-12 18:00
2023-08-12 06:00 | 2023-08-12 12:00 | 2023-08-12 14:00 | 2023-08-12 20:00
2023-08-12 06:00 | 2023-08-12 12:00 | 2023-08-12 14:00 | 2023-08-12 20:00
2023-08-12 09:00 | 2023-08-12 13:00 | 2023-08-12 17:00 | 2023-08-12 21:00
2023-08-12 11:00 | 2023-08-13 02:00 | 2023-08-12 19:00 | 2023-08-13 10:00
2023-08-12 13:00 | 2023-08-12 17:00 | 2023-08-12 21:00 | 2023-08-13 01:00
2023-08-12 14:00 | 2023-08-13 04:00 | 2023-08-12 22:00 | 2023-08-13 12:00
2023-08-12 16:00 | 2023-08-13 00:30 | 2023-08-13 | 2023-08-13 08:30
2023-08-12 17:00 | 2023-08-12 21:00 | 2023-08-13 01:00 | 2023-08-13 05:00
2023-08-12 17:00 | 2023-08-12 21:00 | 2023-08-13 01:00 | 2023-08-13 05:00
2023-08-12 17:00 | 2023-08-12 21:00 | 2023-08-13 01:00 | 2023-08-13 05:00
2023-08-12 18:00 | 2023-08-12 22:00 | 2023-08-13 02:00 | 2023-08-13 06:00
2023-08-12 21:00 | 2023-08-13 01:00 | 2023-08-13 05:00 | 2023-08-13 09:00
2023-08-13 01:00 | 2023-08-13 05:00 | 2023-08-13 09:00 | 2023-08-13 13:00
2023-08-13 02:00 | 2023-08-13 06:00 | 2023-08-13 10:00 | 2023-08-13 14:00
2023-08-13 09:00 | 2023-08-13 13:00 | 2023-08-13 17:00 | 2023-08-13 21:00
2023-08-13 09:00 | 2023-08-13 13:00 | 2023-08-13 17:00 | 2023-08-13 21:00
2023-08-13 10:00 | 2023-08-13 14:00 | 2023-08-13 18:00 | 2023-08-13 22:00
2023-08-13 12:00 | 2023-08-13 16:00 | 2023-08-13 20:00 | 2023-08-14
2023-08-13 16:00 | 2023-08-13 20:00 | 2023-08-14 | 2023-08-14 04:00
Formulas:
PATCH WINDOW (HKT) Start Time = [PATCH WINDOW (GMT) Start Time]+8/24
PATCH WINDOW (HKT)End Time = [PATCH WINDOW (GMT)End Time]+8/24